## Electrification
Potential for Upgradation of stage in STMS- Electrical
Sl. No. | School Name | UDISE-Code | Works Status
|  |  |  | Started | In - Progress |  |  | Completed | Potential for Completion
[5 empty] | Concealed wiring completed | All fixtures fixed | To be shown
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9
1 | AIDED P S LUMBESU | 28120204101 | In-Progress | Yes | Yes | Yes | YES | No
2 | AIDED P S TADIKONDA | 28120202801 | In-Progress | Yes | Yes | No |  | No
3 | GPS JK PADU COLNY | 28120207002 | In-Progress | Yes | Yes | Yes | Yes | No
4 | GPS BEERUPADU | 28120205201 | In-Progress | Yes | Yes | No | Yes | No
5 | GPS CH BINNIDI | 28120204601 | In-Progress | Yes | Yes | No | Yes | No
6 | GPS GEESADA | 28120209501 | In-Progress | Yes | Yes | Yes | Yes | No
7 | GPS LADA | 28120205001 | In-Progress | Yes | Yes | Yes | Yes | Yes
8 | GPS MEDARAGANDA | 28120212303 | In-Progress | Yes | Yes | No | Yes | No
9 | GPS THOLUKHARJA | 28120203901 | In-Progress | Yes | Yes | No |  | No
10 | GPS THOTA | 28120200301 | In-Progress | Yes | Yes | No |  | No
11 | GPS(TW) VADAPUTTI | 28120211901 | In-Progress | Yes | Yes | Yes | Yes | No
12 | GTWAS BHADRAGIRI | 28120207615 | In-Progress | Yes | Yes | No | Yes | No
13 | MPPS DIGUVADERUVADA | 28120211201 | In-Progress | Yes | Yes | No |  | No
14 | MPPS ELWINPETA | 28120207501 | In-Progress | Yes | Yes | Yes | Yes | No
15 | MPPS GORADA | 28120210001 | In-Progress | Yes | Yes | Yes | Yes | No
16 | MPPS GORATI | 28120202401 | In-Progress | Yes | Yes | Yes | Yes | No
17 | MPPS IRIDI | 28120203801 | In-Progress | Yes | Yes | No |  | No
18 | MPPS JARNA | 28120209201 | In-Progress | Yes | Yes | Yes | Yes | No
19 | MPPS KANASINGI | 28120204701 | In-Progress | Yes | Yes | No | Yes | No
20 | MPPS MALLUGUDA | 28120204901 | In-Progress | Yes | Yes | No | Yes | No
21 | MPPS REGIDI | 28120210801 | In-Progress | Yes | Yes | Yes | Yes | Yes
22 | MPPS SAVARAKOTAPADU | 28120207001 | In-Progress | Yes | Yes | Yes | Yes | No
23 | MPPS THATISEELA | 28120207201 | In-Progress | Yes | Yes | No | Yes | No
24 | MPPS VATHADA | 28120207701 | In-Progress | Yes | Yes | No | Yes | No
25 | MPPS Y CHORUPALLI | 28120209301 | In-Progress | Yes | Yes | Yes | Yes | No

## major& minor
Potential for Ugradation of stage in M&M in Phase-II
Sl. No. | School Name | UDISE-Code | Works Status
|  |  |  | Classroom Repairs |  |  |  |  | Toilet repairs
|  |  |  | Started | In - Progress |  |  | Completed | Not Started | Started | In - Progress |  |  | Completed
[5 empty] | Civil work inprogress | Work Completed except Doors and windows fixing | To be shown |  |  |  | Civil work inprogress | Work Completed except doors fixing | To be shown
1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | AIDED P S LUMBESU | 28120204101 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
2 | AIDED P S LUMBESU | 28120204101 | Mou Signed | No | No | No |  | No | No | No | No | No |  | No
3 | AIDED P S TADIKONDA | 28120202801 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | Yes |  | Yes
4 | AIDED P S TADIKONDA | 28120202801 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
5 | GPS JK PADU COLNY | 28120207002 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
6 | GPS JK PADU COLNY | 28120207002 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
7 | GPS BEERUPADU | 28120205201 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
8 | GPS BEERUPADU | 28120205201 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
9 | GPS CH BINNIDI | 28120204601 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
10 | GPS CH BINNIDI | 28120204601 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
11 | GPS GEESADA | 28120209501 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
12 | GPS GEESADA | 28120209501 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
13 | GPS LADA | 28120205001 | In-Progress | Yes | Yes | Yes | Yes | Yes | No | No | No | No |  | No
14 | GPS LADA | 28120205001 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
15 | GPS MEDARAGANDA | 28120212303 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
16 | GPS MEDARAGANDA | 28120212303 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
17 | GPS THOLUKHARJA | 28120203901 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
18 | GPS THOLUKHARJA | 28120203901 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
19 | GPS THOTA | 28120200301 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | Yes |  | Yes
20 | GPS THOTA | 28120200301 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
21 | GPS(TW) VADAPUTTI | 28120211901 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
22 | GPS(TW) VADAPUTTI | 28120211901 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
23 | GTWAS BHADRAGIRI | 28120207615 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | Yes | Yes | Yes
24 | GTWAS BHADRAGIRI | 28120207615 | In-Progress | No | No | No | Yes | No | No | No | No | No |  | No
25 | MPPS BAYYADA | 28120209801 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
26 | MPPS BAYYADA | 28120209801 | Mou Signed | No | No | No |  | No | No | No | No | No |  | No
27 | MPPS DIGUVADERUVADA | 28120211201 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
28 | MPPS DIGUVADERUVADA | 28120211201 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
29 | MPPS ELWINPETA | 28120207501 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
30 | MPPS ELWINPETA | 28120207501 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
31 | MPPS GORADA | 28120210001 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
32 | MPPS GORADA | 28120210001 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
33 | MPPS GORATI | 28120202401 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
34 | MPPS GORATI | 28120202401 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
35 | MPPS IRIDI | 28120203801 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
36 | MPPS IRIDI | 28120203801 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
37 | MPPS JARNA | 28120209201 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
38 | MPPS JARNA | 28120209201 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
39 | MPPS KANASINGI | 28120204701 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
40 | MPPS KANASINGI | 28120204701 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
41 | MPPS MALLUGUDA | 28120204901 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
42 | MPPS MALLUGUDA | 28120204901 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
43 | MPPS REGIDI | 28120210801 | In-Progress | Yes | Yes | Yes | Yes | Yes | No | No | No | No |  | No
44 | MPPS REGIDI | 28120210801 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
45 | MPPS SAVARAKOTAPADU | 28120207001 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
46 | MPPS SAVARAKOTAPADU | 28120207001 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No | Yes | No
47 | MPPS THATISEELA | 28120207201 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
48 | MPPS THATISEELA | 28120207201 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
49 | MPPS VATHADA | 28120207701 | In-Progress | Yes | Yes | No | Yes | No | No | No | No | No |  | No
50 | MPPS VATHADA | 28120207701 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No
51 | MPPS Y CHORUPALLI | 28120209301 | In-Progress | Yes | Yes | No |  | No | No | No | No | No |  | No
52 | MPPS Y CHORUPALLI | 28120209301 | In-Progress | No | No | No |  | No | Yes | Yes | Yes | No |  | No