## Combined
R1.2 Component Wise Status Report as on (31-Jul-2023 11:04:00)
School Name : AIDED P S LUMBESU | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | RF CREDITED
1 | Construction of Toilet with Running Water | 1 | 4.53 | 1 | 4.53 | 0.83 |  |  |  |  | AIDED P S LUMBESU
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.41 | 0 | 0 | 0.06 |  |  |  |  | AIDED P S LUMBESU
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 1.95 |  |  |  |  | AIDED P S LUMBESU
4 | Furniture for Students and Staff | 1 | 1.46 | 0 | 0 | 0 |  |  |  |  | AIDED P S LUMBESU
5 | Painting to School | 1 | 0.35 | 0 | 0 | 0 |  |  |  |  | AIDED P S LUMBESU
6 | Major and Minor Repairs | 1 | 2.88 | 0 | 0 | 0 |  |  |  |  | AIDED P S LUMBESU
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | AIDED P S LUMBESU
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 4.63 |  |  |  |  | AIDED P S LUMBESU
9 | Kitchen Shed | 1 | 1.77 | 0 | 0 | 0 |  |  |  |  | AIDED P S LUMBESU
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | AIDED P S LUMBESU
11 | Total | 9 | 24.92 | 3 | 17.78 | 7.46 | 7.13 | 7.48 | -0.35 |  | AIDED P S LUMBESU
School Name : MPPS KANASINGI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS KANASINGI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS KANASINGI
1 | Construction of Toilet with Running Water | 1 | 4.4 | 1 | 4.4 | 4.69 |  |  |  |  | MPPS KANASINGI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.71 | 0 | 0 | 0.28 |  |  |  |  | MPPS KANASINGI
3 | Drinking Water Supply | 1 | 0.34 | 1 | 0.34 | 0.53 |  |  |  |  | MPPS KANASINGI
4 | Furniture for Students and Staff | 1 | 1.91 | 0 | 0 | 0 |  |  |  |  | MPPS KANASINGI
5 | Painting to School | 1 | 1.28 | 0 | 0 | 0 |  |  |  |  | MPPS KANASINGI
6 | Major and Minor Repairs | 1 | 2.31 | 1 | 2.31 | 2.78 |  |  |  |  | MPPS KANASINGI
7 | Green Chalk Boards | 1 | 0.53 | 0 | 0 | 0 |  |  |  |  | MPPS KANASINGI
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS KANASINGI
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS KANASINGI
10 | Total | 8 | 12 | 3 | 7.06 | 8.28 | 3.28 | 3.3 | -0.02 |  | MPPS KANASINGI
School Name : GPS LADA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS LADA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS LADA
1 | Construction of Toilet with Running Water | 1 | 4.64 | 1 | 4.64 | 1.96 |  |  |  |  | GPS LADA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.46 | 0 | 0 | 0.21 |  |  |  |  | GPS LADA
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.5 |  |  |  |  | GPS LADA
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 |  |  |  |  | GPS LADA
5 | Painting to School | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS LADA
6 | Major and Minor Repairs | 1 | 1.33 | 1 | 1.33 | 1.1 |  |  |  |  | GPS LADA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS LADA
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS LADA
9 | Kitchen Shed | 1 | 1.68 | 1 | 1.68 | 1.68 |  |  |  |  | GPS LADA
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | GPS LADA
11 | Total | 9 | 11.98 | 4 | 7.9 | 5.46 | 3.68 | 3.72 | -0.04 |  | GPS LADA
School Name : GPS THOTA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS THOTA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS THOTA
1 | Construction of Toilet with Running Water | 1 | 4.58 | 1 | 4.58 | 1 |  |  |  |  | GPS THOTA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.33 | 0 | 0 | 0.18 |  |  |  |  | GPS THOTA
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
5 | Painting to School | 1 | 0.42 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
6 | Major and Minor Repairs | 1 | 2.07 | 1 | 2.07 | 3.34 |  |  |  |  | GPS THOTA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
9 | Kitchen Shed | 1 | 1.2 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | GPS THOTA
11 | Total | 9 | 11.98 | 2 | 6.66 | 4.51 | 2.42 | 2.53 | -0.11 |  | GPS THOTA
School Name : MPPS SAVARAKOTAPADU | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS SAVARAKOTAPADU
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS SAVARAKOTAPADU
1 | Construction of Toilet with Running Water | 1 | 4.94 | 1 | 4.94 | 3.18 |  |  |  |  | MPPS SAVARAKOTAPADU
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.64 | 1 | 0.64 | 0.59 |  |  |  |  | MPPS SAVARAKOTAPADU
3 | Drinking Water Supply | 1 | 0.9 | 1 | 0.9 | 0.01 |  |  |  |  | MPPS SAVARAKOTAPADU
4 | Furniture for Students and Staff | 1 | 1.43 | 0 | 0 | 0 |  |  |  |  | MPPS SAVARAKOTAPADU
5 | Painting to School | 1 | 0.71 | 0 | 0 | 0 |  |  |  |  | MPPS SAVARAKOTAPADU
6 | Major and Minor Repairs | 1 | 2.59 | 1 | 2.59 | 2.07 |  |  |  |  | MPPS SAVARAKOTAPADU
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS SAVARAKOTAPADU
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS SAVARAKOTAPADU
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS SAVARAKOTAPADU
10 | Total | 8 | 12 | 4 | 9.08 | 5.85 | 3.11 | 3.25 | -0.14 |  | MPPS SAVARAKOTAPADU
School Name : GPS JK PADU COLNY
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS JK PADU COLNY
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS JK PADU COLNY
1 | Construction of Toilet with Running Water | 1 | 5.33 | 1 | 5.33 | 1.44 |  |  |  |  | GPS JK PADU COLNY
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.8 | 1 | 0.8 | 1.18 |  |  |  |  | GPS JK PADU COLNY
3 | Drinking Water Supply | 1 | 0.9 | 0 | 0 | 0 |  |  |  |  | GPS JK PADU COLNY
4 | Furniture for Students and Staff | 1 | 1.47 | 0 | 0 | 0 |  |  |  |  | GPS JK PADU COLNY
5 | Painting to School | 1 | 0.73 | 0 | 0 | 0 |  |  |  |  | GPS JK PADU COLNY
6 | Major and Minor Repairs | 1 | 5.8 | 1 | 5.8 | 4.05 |  |  |  |  | GPS JK PADU COLNY
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 |  |  |  |  | GPS JK PADU COLNY
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS JK PADU COLNY
9 | Total | 8 | 15.94 | 3 | 11.93 | 6.67 | 4.05 | 4.19 | -0.14 |  | GPS JK PADU COLNY
School Name : MPPS THATISEELA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS THATISEELA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS THATISEELA
1 | Construction of Toilet with Running Water | 1 | 4.68 | 1 | 4.68 | 3.55 |  |  |  |  | MPPS THATISEELA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.78 | 0 | 0 | 0.25 |  |  |  |  | MPPS THATISEELA
3 | Drinking Water Supply | 1 | 0.93 | 0 | 0 | 0 |  |  |  |  | MPPS THATISEELA
4 | Furniture for Students and Staff | 1 | 1.83 | 0 | 0 | 0 |  |  |  |  | MPPS THATISEELA
5 | Painting to School | 1 | 1.03 | 0 | 0 | 0 |  |  |  |  | MPPS THATISEELA
6 | Major and Minor Repairs | 1 | 1.93 | 1 | 1.93 | 2.52 |  |  |  |  | MPPS THATISEELA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS THATISEELA
8 | Construction of Compound Walls | 1 | 7.29 | 0 | 0 | 0 |  |  |  |  | MPPS THATISEELA
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS THATISEELA
10 | Total | 9 | 19.24 | 2 | 6.61 | 6.31 | 4.33 | 4.49 | -0.16 |  | MPPS THATISEELA
School Name : MPPS DIGUVADERUVADA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS DIGUVADERUVADA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS DIGUVADERUVADA
1 | Construction of Toilet with Running Water | 1 | 7.51 | 1 | 7.51 | 0.4 |  |  |  |  | MPPS DIGUVADERUVADA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.74 |  |  |  |  | MPPS DIGUVADERUVADA
4 | Furniture for Students and Staff | 1 | 2.89 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
5 | Painting to School | 1 | 0.47 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
6 | Major and Minor Repairs | 1 | 0.53 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 25.99 | 1 | 25.99 | 10.32 |  |  |  |  | MPPS DIGUVADERUVADA
9 | Construction of Compound Walls | 1 | 15 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
10 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
11 | Kitchen Shed | 1 | 3.19 | 0 | 0 | 0.28 |  |  |  |  | MPPS DIGUVADERUVADA
12 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS DIGUVADERUVADA
13 | Total | 11 | 56.99 | 3 | 33.76 | 11.75 | 14.91 | 9.97 | 4.94 |  | MPPS DIGUVADERUVADA
School Name : MPPS MALLUGUDA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS MALLUGUDA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS MALLUGUDA
1 | Construction of Toilet with Running Water | 1 | 5.66 | 1 | 5.66 | 0.54 |  |  |  |  | MPPS MALLUGUDA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.61 | 0 | 0 | 0.17 |  |  |  |  | MPPS MALLUGUDA
3 | Drinking Water Supply | 1 | 0.67 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
4 | Furniture for Students and Staff | 1 | 2.79 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
5 | Painting to School | 1 | 0.68 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
6 | Major and Minor Repairs | 1 | 0.72 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 23.84 | 1 | 23.84 | 9.1 |  |  |  |  | MPPS MALLUGUDA
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
10 | Kitchen Shed | 1 | 3.57 | 0 | 0 | 0.24 |  |  |  |  | MPPS MALLUGUDA
11 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS MALLUGUDA
12 | Total | 10 | 39.45 | 2 | 29.5 | 10.05 | 10.59 | 7.28 | 3.31 |  | MPPS MALLUGUDA
School Name : MPPS GORATI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS GORATI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS GORATI
1 | Construction of Toilet with Running Water | 1 | 4.52 | 1 | 4.52 | 0.59 |  |  |  |  | MPPS GORATI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0.06 |  |  |  |  | MPPS GORATI
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
5 | Painting to School | 1 | 0.35 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
6 | Major and Minor Repairs | 1 | 2.17 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 4.39 |  |  |  |  | MPPS GORATI
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
10 | Kitchen Shed | 1 | 1.18 | 0 | 0 | 0 |  |  |  |  | MPPS GORATI
11 | Total | 10 | 24.97 | 2 | 17.52 | 5.04 | 7.42 | 3.94 | 3.48 |  | MPPS GORATI
School Name : GPS(TW) VADAPUTTI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS(TW) VADAPUTTI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS(TW) VADAPUTTI
1 | Construction of Toilet with Running Water | 1 | 7.88 | 1 | 7.88 | 1.39 |  |  |  |  | GPS(TW) VADAPUTTI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.49 | 0 | 0 | 0.06 |  |  |  |  | GPS(TW) VADAPUTTI
3 | Drinking Water Supply | 1 | 0.85 | 0 | 0 | 0 |  |  |  |  | GPS(TW) VADAPUTTI
4 | Furniture for Students and Staff | 1 | 2.78 | 0 | 0 | 0 |  |  |  |  | GPS(TW) VADAPUTTI
5 | Painting to School | 1 | 0.5 | 0 | 0 | 0 |  |  |  |  | GPS(TW) VADAPUTTI
6 | Major and Minor Repairs | 1 | 2.07 | 1 | 2.07 | 0.58 |  |  |  |  | GPS(TW) VADAPUTTI
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS(TW) VADAPUTTI
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 2.48 |  |  |  |  | GPS(TW) VADAPUTTI
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS(TW) VADAPUTTI
10 | Kitchen Shed | 1 | 0.64 | 1 | 0.64 | 0.07 |  |  |  |  | GPS(TW) VADAPUTTI
11 | Total | 10 | 28.99 | 4 | 23.59 | 4.58 | 5.22 | 2.47 | 2.75 |  | GPS(TW) VADAPUTTI
School Name : GPS BEERUPADU | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS BEERUPADU
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS BEERUPADU
1 | Construction of Toilet with Running Water | 1 | 4.49 | 1 | 4.49 | 1.21 |  |  |  |  | GPS BEERUPADU
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0.27 |  |  |  |  | GPS BEERUPADU
3 | Drinking Water Supply | 1 | 0.31 | 1 | 0.31 | 0.58 |  |  |  |  | GPS BEERUPADU
4 | Furniture for Students and Staff | 1 | 1.47 | 0 | 0 | 0 |  |  |  |  | GPS BEERUPADU
5 | Painting to School | 1 | 0.9 | 0 | 0 | 0 |  |  |  |  | GPS BEERUPADU
6 | Major and Minor Repairs | 1 | 2.03 | 1 | 2.03 | 1.47 |  |  |  |  | GPS BEERUPADU
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS BEERUPADU
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS BEERUPADU
9 | Kitchen Shed | 1 | 1.63 | 1 | 1.63 | 0.48 |  |  |  |  | GPS BEERUPADU
10 | Total | 9 | 11.98 | 4 | 8.46 | 4.02 | 3.08 | 1.86 | 1.22 |  | GPS BEERUPADU
School Name : GPS THOLUKHARJA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS THOLUKHARJA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS THOLUKHARJA
1 | Construction of Toilet with Running Water | 1 | 5.41 | 1 | 5.41 | 1.57 |  |  |  |  | GPS THOLUKHARJA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.34 | 0 | 0 | 0.06 |  |  |  |  | GPS THOLUKHARJA
3 | Drinking Water Supply | 1 | 0.52 | 0 | 0 | 0 |  |  |  |  | GPS THOLUKHARJA
4 | Furniture for Students and Staff | 1 | 1.24 | 0 | 0 | 0 |  |  |  |  | GPS THOLUKHARJA
5 | Painting to School | 1 | 0.25 | 0 | 0 | 0 |  |  |  |  | GPS THOLUKHARJA
6 | Major and Minor Repairs | 1 | 1.1 | 0 | 0 | 0 |  |  |  |  | GPS THOLUKHARJA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS THOLUKHARJA
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 12.99 | 1 | 12.99 | 4.83 |  |  |  |  | GPS THOLUKHARJA
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS THOLUKHARJA
10 | Kitchen Shed | 1 | 2.34 | 1 | 2.34 | 0.12 |  |  |  |  | GPS THOLUKHARJA
11 | Total | 10 | 24.99 | 3 | 20.75 | 6.58 | 7.29 | 4.73 | 2.56 |  | GPS THOLUKHARJA
School Name : MPPS BAYYADA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS BAYYADA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS BAYYADA
1 | Construction of Toilet with Running Water | 1 | 6.25 | 1 | 6.25 | 0.76 |  |  |  |  | MPPS BAYYADA
2 | Drinking Water Supply | 1 | 0.79 | 0 | 0 | 0 |  |  |  |  | MPPS BAYYADA
3 | Furniture for Students and Staff | 1 | 1.8 | 0 | 0 | 0 |  |  |  |  | MPPS BAYYADA
4 | Major and Minor Repairs | 1 | 2.38 | 0 | 0 | 0 |  |  |  |  | MPPS BAYYADA
5 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS BAYYADA
6 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 25.98 | 1 | 25.98 | 11.29 |  |  |  |  | MPPS BAYYADA
7 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS BAYYADA
8 | Multiple Works Expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS BAYYADA
9 | Total | 7 | 37.98 | 2 | 32.24 | 12.04 | 10.55 | 8.87 | 1.68 |  | MPPS BAYYADA
School Name : AIDED P S TADIKONDA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | AIDED P S TADIKONDA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | AIDED P S TADIKONDA
1 | Construction of Toilet with Running Water | 1 | 5.58 | 1 | 5.58 | 2.23 |  |  |  |  | AIDED P S TADIKONDA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.41 | 0 | 0 | 0.06 |  |  |  |  | AIDED P S TADIKONDA
3 | Drinking Water Supply | 1 | 0.44 | 1 | 0.44 | 0.55 |  |  |  |  | AIDED P S TADIKONDA
4 | Furniture for Students and Staff | 1 | 2.57 | 0 | 0 | 0 |  |  |  |  | AIDED P S TADIKONDA
5 | Painting to School | 1 | 0.42 | 0 | 0 | 0 |  |  |  |  | AIDED P S TADIKONDA
6 | Major and Minor Repairs | 1 | 2.32 | 0 | 0 | 0 |  |  |  |  | AIDED P S TADIKONDA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | AIDED P S TADIKONDA
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 5.16 |  |  |  |  | AIDED P S TADIKONDA
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | AIDED P S TADIKONDA
10 | Total | 8 | 25 | 3 | 19.02 | 8 | 6.89 | 6.97 | -0.08 |  | AIDED P S TADIKONDA
School Name : MPPS Y CHORUPALLI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS Y CHORUPALLI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS Y CHORUPALLI
1 | Construction of Toilet with Running Water | 1 | 4.89 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.37 | 0 | 0 | 0.06 |  |  |  |  | MPPS Y CHORUPALLI
3 | Drinking Water Supply | 1 | 0.52 | 1 | 0.52 | 0.82 |  |  |  |  | MPPS Y CHORUPALLI
4 | Furniture for Students and Staff | 1 | 1.58 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
5 | Painting to School | 1 | 0.41 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
6 | Major and Minor Repairs | 1 | 1.04 | 1 | 1.04 | 0.52 |  |  |  |  | MPPS Y CHORUPALLI
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 5.23 |  |  |  |  | MPPS Y CHORUPALLI
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
10 | Kitchen Shed | 1 | 2.41 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
11 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS Y CHORUPALLI
12 | Total | 10 | 24.99 | 3 | 14.56 | 6.63 | 6.77 | 6.6 | 0.17 |  | MPPS Y CHORUPALLI
School Name : MPPS VATHADA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS VATHADA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS VATHADA
1 | Construction of Toilet with Running Water | 1 | 4.55 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.34 | 0 | 0 | 0.05 |  |  |  |  | MPPS VATHADA
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
4 | Furniture for Students and Staff | 1 | 2.25 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
5 | Painting to School | 1 | 0.3 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
6 | Major and Minor Repairs | 1 | 2.19 | 1 | 2.19 | 1.46 |  |  |  |  | MPPS VATHADA
7 | Green Chalk Boards | 1 | 0.53 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 5.22 |  |  |  |  | MPPS VATHADA
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
10 | Kitchen Shed | 1 | 1.08 | 0 | 0 | 0 |  |  |  |  | MPPS VATHADA
11 | Total | 10 | 25 | 2 | 15.19 | 6.73 | 5.71 | 5.58 | 0.13 |  | MPPS VATHADA
School Name : GTWAS BHADRAGIRI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GTWAS BHADRAGIRI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GTWAS BHADRAGIRI
1 | Construction of Toilet with Running Water | 1 | 17.77 | 1 | 17.77 | 14.34 |  |  |  |  | GTWAS BHADRAGIRI
2 | Providing Electrification with Fans and Tube Lights | 1 | 4.69 | 1 | 4.69 | 3.18 |  |  |  |  | GTWAS BHADRAGIRI
3 | Drinking Water Supply | 1 | 1.27 | 1 | 1.27 | 0.99 |  |  |  |  | GTWAS BHADRAGIRI
4 | Furniture for Students and Staff | 1 | 17.76 | 1 | 17.76 | 9.39 |  |  |  |  | GTWAS BHADRAGIRI
5 | Painting to School | 1 | 7.63 | 0 | 0 | 0 |  |  |  |  | GTWAS BHADRAGIRI
6 | Major and Minor Repairs | 1 | 17.32 | 1 | 17.32 | 7.46 |  |  |  |  | GTWAS BHADRAGIRI
7 | Green Chalk Boards | 1 | 1.06 | 0 | 0 | 0 |  |  |  |  | GTWAS BHADRAGIRI
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 60.99 | 1 | 60.99 | 12.3 |  |  |  |  | GTWAS BHADRAGIRI
9 | Construction of Compound Walls | 1 | 13.49 | 0 | 0 | 0 |  |  |  |  | GTWAS BHADRAGIRI
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | GTWAS BHADRAGIRI
11 | Total | 9 | 141.99 | 6 | 119.8 | 47.67 | 31.85 | 32.99 | -1.14 |  | GTWAS BHADRAGIRI
School Name : MPPS IRIDI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS IRIDI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS IRIDI
1 | Construction of Toilet with Running Water | 1 | 4.47 | 1 | 4.47 | 1.66 |  |  |  |  | MPPS IRIDI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.37 | 0 | 0 | 0.17 |  |  |  |  | MPPS IRIDI
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 |  |  |  |  | MPPS IRIDI
4 | Furniture for Students and Staff | 1 | 3.23 | 0 | 0 | 0 |  |  |  |  | MPPS IRIDI
5 | Painting to School | 1 | 0.37 | 0 | 0 | 0 |  |  |  |  | MPPS IRIDI
6 | Major and Minor Repairs | 1 | 1.21 | 0 | 0 | 0 |  |  |  |  | MPPS IRIDI
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 |  |  |  |  | MPPS IRIDI
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 37 | 1 | 37 | 2.87 |  |  |  |  | MPPS IRIDI
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS IRIDI
10 | Kitchen Shed | 1 | 1.19 | 1 | 1.19 | 1.23 |  |  |  |  | MPPS IRIDI
11 | Total | 10 | 49 | 3 | 42.66 | 5.93 | 1.8 | 3.53 | -1.73 |  | MPPS IRIDI
School Name : GPS MEDARAGANDA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS MEDARAGANDA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS MEDARAGANDA
1 | Construction of Toilet with Running Water | 1 | 4.64 | 1 | 4.64 | 4.1 |  |  |  |  | GPS MEDARAGANDA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0.24 |  |  |  |  | GPS MEDARAGANDA
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.34 |  |  |  |  | GPS MEDARAGANDA
4 | Furniture for Students and Staff | 1 | 1.91 | 0 | 0 | 0 |  |  |  |  | GPS MEDARAGANDA
5 | Painting to School | 1 | 0.41 | 0 | 0 | 0 |  |  |  |  | GPS MEDARAGANDA
6 | Major and Minor Repairs | 1 | 2.1 | 1 | 2.1 | 1.58 |  |  |  |  | GPS MEDARAGANDA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS MEDARAGANDA
8 | Construction of Compound Walls | 1 | 10.12 | 0 | 0 | 0 |  |  |  |  | GPS MEDARAGANDA
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS MEDARAGANDA
10 | Kitchen Shed | 1 | 1.51 | 1 | 1.51 | 1.01 |  |  |  |  | GPS MEDARAGANDA
11 | Total | 10 | 22.1 | 4 | 8.5 | 7.27 | 4.82 | 4.87 | -0.05 |  | GPS MEDARAGANDA
School Name : MPPS GORADA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS GORADA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS GORADA
1 | Construction of Toilet with Running Water | 1 | 5.24 | 1 | 5.24 | 3.24 |  |  |  |  | MPPS GORADA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.36 | 0 | 0 | 0.42 |  |  |  |  | MPPS GORADA
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 |  |  |  |  | MPPS GORADA
4 | Furniture for Students and Staff | 1 | 2.24 | 0 | 0 | 0 |  |  |  |  | MPPS GORADA
5 | Painting to School | 1 | 1.12 | 0 | 0 | 0 |  |  |  |  | MPPS GORADA
6 | Major and Minor Repairs | 1 | 2 | 1 | 2 | 1.87 |  |  |  |  | MPPS GORADA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS GORADA
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS GORADA
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS GORADA
10 | Total | 8 | 11.98 | 2 | 7.24 | 5.53 | 3.14 | 2.76 | 0.38 |  | MPPS GORADA
School Name : MPPS JARNA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS JARNA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS JARNA
1 | Construction of Toilet with Running Water | 1 | 5.37 | 1 | 5.37 | 0.95 |  |  |  |  | MPPS JARNA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.34 | 0 | 0 | 0.16 |  |  |  |  | MPPS JARNA
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.47 |  |  |  |  | MPPS JARNA
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 |  |  |  |  | MPPS JARNA
5 | Painting to School | 1 | 0.48 | 0 | 0 | 0 |  |  |  |  | MPPS JARNA
6 | Major and Minor Repairs | 1 | 1.23 | 1 | 1.23 | 1.91 |  |  |  |  | MPPS JARNA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS JARNA
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS JARNA
9 | Kitchen Shed | 1 | 1.21 | 1 | 1.21 | 0.22 |  |  |  |  | MPPS JARNA
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS JARNA
11 | Total | 9 | 11.99 | 4 | 8.05 | 3.72 | 2.57 | 2.29 | 0.28 |  | MPPS JARNA
School Name : GPS GEESADA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS GEESADA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS GEESADA
1 | Construction of Toilet with Running Water | 1 | 4.28 | 1 | 4.28 | 2.68 |  |  |  |  | GPS GEESADA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.53 | 1 | 0.53 | 0.3 |  |  |  |  | GPS GEESADA
3 | Drinking Water Supply | 1 | 0.19 | 0 | 0 | 0 |  |  |  |  | GPS GEESADA
4 | Furniture for Students and Staff | 1 | 1.61 | 0 | 0 | 0 |  |  |  |  | GPS GEESADA
5 | Painting to School | 1 | 1.06 | 0 | 0 | 0 |  |  |  |  | GPS GEESADA
6 | Major and Minor Repairs | 1 | 2.4 | 1 | 2.4 | 1.75 |  |  |  |  | GPS GEESADA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | GPS GEESADA
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS GEESADA
9 | Kitchen Shed | 1 | 1.14 | 1 | 1.14 | 1.15 |  |  |  |  | GPS GEESADA
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | GPS GEESADA
11 | Total | 9 | 11.99 | 4 | 8.35 | 5.88 | 3.61 | 3.55 | 0.06 |  | GPS GEESADA
School Name : MPPS REGIDI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS REGIDI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS REGIDI
1 | Construction of Toilet with Running Water | 1 | 7.79 | 1 | 7.79 | 2.66 |  |  |  |  | MPPS REGIDI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.78 | 1 | 0.78 | 0.29 |  |  |  |  | MPPS REGIDI
3 | Drinking Water Supply | 1 | 0.85 | 0 | 0 | 0 |  |  |  |  | MPPS REGIDI
4 | Furniture for Students and Staff | 1 | 3.01 | 0 | 0 | 0 |  |  |  |  | MPPS REGIDI
5 | Painting to School | 1 | 1.72 | 0 | 0 | 0 |  |  |  |  | MPPS REGIDI
6 | Major and Minor Repairs | 1 | 0.61 | 1 | 0.61 | 4.05 |  |  |  |  | MPPS REGIDI
7 | Green Chalk Boards | 1 | 0.66 | 0 | 0 | 0 |  |  |  |  | MPPS REGIDI
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS REGIDI
9 | Total | 8 | 15.93 | 3 | 9.18 | 7 | 4.8 | 4.7 | 0.1 |  | MPPS REGIDI
School Name : MPPS ELWINPETA | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | MPPS ELWINPETA
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | MPPS ELWINPETA
1 | Construction of Toilet with Running Water | 1 | 5.04 | 1 | 5.04 | 2.9 |  |  |  |  | MPPS ELWINPETA
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.59 | 0 | 0 | 0.26 |  |  |  |  | MPPS ELWINPETA
3 | Drinking Water Supply | 1 | 0.9 | 0 | 0 | 0 |  |  |  |  | MPPS ELWINPETA
4 | Furniture for Students and Staff | 1 | 1.32 | 0 | 0 | 0 |  |  |  |  | MPPS ELWINPETA
5 | Painting to School | 1 | 1.26 | 0 | 0 | 0 |  |  |  |  | MPPS ELWINPETA
6 | Major and Minor Repairs | 1 | 2.11 | 1 | 2.11 | 1.45 |  |  |  |  | MPPS ELWINPETA
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 |  |  |  |  | MPPS ELWINPETA
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | MPPS ELWINPETA
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MPPS ELWINPETA
10 | Total | 8 | 11.99 | 2 | 7.14 | 4.61 | 3.53 | 3.51 | 0.02 |  | MPPS ELWINPETA
School Name : GPS CH BINNIDI | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | GPS CH BINNIDI
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | GPS CH BINNIDI
1 | Construction of Toilet with Running Water | 1 | 4.97 | 1 | 4.97 | 3.67 |  |  |  |  | GPS CH BINNIDI
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.58 | 0 | 0 | 0.17 |  |  |  |  | GPS CH BINNIDI
3 | Drinking Water Supply | 1 | 0.28 | 1 | 0.28 | 0.44 |  |  |  |  | GPS CH BINNIDI
4 | Furniture for Students and Staff | 1 | 1.25 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
5 | Painting to School | 1 | 0.47 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
6 | Major and Minor Repairs | 1 | 2.57 | 1 | 2.57 | 2.11 |  |  |  |  | GPS CH BINNIDI
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
8 | Construction of Compound Walls | 1 | 7.5 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
10 | Kitchen Shed | 1 | 0.95 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
11 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | GPS CH BINNIDI
12 | Total | 10 | 19.48 | 3 | 7.82 | 6.39 | 4.72 | 4.73 | -0.01 |  | GPS CH BINNIDI
Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All | [6 empty] | RF CREDITED AS ON 31-07-2023 | EXPENDITURE AS OF NOW | Balance Amount tobe Spent | Remarks
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details | [6 empty] | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
1 | Construction of Toilet with Running Water | 14079 | 83521.01 | 13693 | 82250.36 | 51911.93 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
2 | Providing Electrification with Fans and Tube Lights | 14023 | 19349.05 | 11427 | 16546.22 | 9175.45 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
3 | Drinking Water Supply | 14208 | 33304.83 | 8292 | 21239.41 | 5349.02 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
4 | Furniture for Students and Staff | 14131 | 51895.84 | 8318 | 34720.84 | 24388.61 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
5 | Painting to School | 14083 | 28221.08 | 41 | 147.75 | 11.15 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
6 | Major and Minor Repairs | 14023 | 70857.96 | 12874 | 67868.45 | 38496.1 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
7 | Green Chalk Boards | 14091 | 8100.41 | 674 | 361.67 | 185.75 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 8886 | 378900.13 | 8636 | 370769.62 | 120694.33 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
9 | Construction of Compound Walls | 5998 | 52459.5 | 4525 | 40493.84 | 9876.07 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
10 | English Labs | 8018 | 4089.18 | 129 | 65.79 | 26.42 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
11 | Kitchen Shed | 9231 | 20733.61 | 6369 | 16674.11 | 8362.45 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
12 | Co-Located Anganwadi Centers | 4399 | 14822.26 | 4384 | 14781.72 | 1932.75 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
13 | Multiple Works Expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
14 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
15 | Total | 135170 | 766254.86 | 79362 | 665919.8 | 270410.02 | 167.27 | 150.16 | 17.11 |  | Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All

## 1
R1.2 Component Wise Status Report as on (31-Jul-2023 11:04:00)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : AIDED P S LUMBESU
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.53 | 1 | 4.53 | 0.83 | 0 (0%) | 0 | 0 | 0.83
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.41 | 0 | 0 | 0.06 | 0 (0%) | 0 | 0 | 0.06
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 1.95 | 0 (0%) | 0 | 0 | 1.95
4 | Furniture for Students and Staff | 1 | 1.46 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.35 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.88 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 4.63 | 0 (0%) | 0 | 0 | 4.63
9 | Kitchen Shed | 1 | 1.77 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.07
11 | Total | 9 | 24.92 | 3 | 17.78 | 7.46 | 0 (0%) | 0 | 0 | 7.53

## 10
R1.2 Component Wise Status Report as on (31-Jul-2023 11:08:20)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS KANASINGI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.4 | 1 | 4.4 | 4.69 | 0 (0%) | 0 | 0 | 4.69
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.71 | 0 | 0 | 0.28 | 0 (0%) | 0 | 0 | 0.28
3 | Drinking Water Supply | 1 | 0.34 | 1 | 0.34 | 0.53 | 0 (0%) | 0 | 0 | 0.53
4 | Furniture for Students and Staff | 1 | 1.91 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 1.28 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.31 | 1 | 2.31 | 2.78 | 0 (0%) | 0 | 0 | 2.78
7 | Green Chalk Boards | 1 | 0.53 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.02
10 | Total | 8 | 12 | 3 | 7.06 | 8.28 | 0 (0%) | 0 | 0 | 8.3

## 11
R1.2 Component Wise Status Report as on (31-Jul-2023 11:08:42)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS LADA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.64 | 1 | 4.64 | 1.96 | 0 (0%) | 0 | 0 | 1.96
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.46 | 0 | 0 | 0.21 | 0 (0%) | 0 | 0 | 0.21
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.5 | 0 (0%) | 0 | 0 | 0.5
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 1.33 | 1 | 1.33 | 1.1 | 0 (0%) | 0 | 0 | 1.1
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Kitchen Shed | 1 | 1.68 | 1 | 1.68 | 1.68 | 0 (0%) | 0 | 0 | 1.68
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01
11 | Total | 9 | 11.98 | 4 | 7.9 | 5.46 | 0 (0%) | 0 | 0 | 5.47

## 12
R1.2 Component Wise Status Report as on (31-Jul-2023 11:08:58)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS THOTA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.58 | 1 | 4.58 | 1 | 0 (0%) | 0 | 0 | 1
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.33 | 0 | 0 | 0.18 | 0 (0%) | 0 | 0 | 0.18
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.42 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.07 | 1 | 2.07 | 3.34 | 0 (0%) | 0 | 0 | 3.34
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Kitchen Shed | 1 | 1.2 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01
11 | Total | 9 | 11.98 | 2 | 6.66 | 4.51 | 0 (0%) | 0 | 0 | 4.52

## 13
R1.2 Component Wise Status Report as on (31-Jul-2023 11:09:14)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS SAVARAKOTAPADU
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.94 | 1 | 4.94 | 3.18 | 0 (0%) | 0 | 0 | 3.18
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.64 | 1 | 0.64 | 0.59 | 0 (0%) | 0 | 0 | 0.59
3 | Drinking Water Supply | 1 | 0.9 | 1 | 0.9 | 0.01 | 0 (0%) | 0 | 0 | 0.01
4 | Furniture for Students and Staff | 1 | 1.43 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.71 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.59 | 1 | 2.59 | 2.07 | 0 (0%) | 0 | 0 | 2.07
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01
10 | Total | 8 | 12 | 4 | 9.08 | 5.85 | 0 (0%) | 0 | 0 | 5.86

## 14
R1.2 Component Wise Status Report as on (31-Jul-2023 11:09:28)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS JK PADU COLNY
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.33 | 1 | 5.33 | 1.44 | 0 (0%) | 0 | 0 | 1.44
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.8 | 1 | 0.8 | 1.18 | 0 (0%) | 0 | 0 | 1.18
3 | Drinking Water Supply | 1 | 0.9 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 1.47 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.73 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 5.8 | 1 | 5.8 | 4.05 | 0 (0%) | 0 | 0 | 4.05
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Total | 8 | 15.94 | 3 | 11.93 | 6.67 | 0 (0%) | 0 | 0 | 6.67

## 15
R1.2 Component Wise Status Report as on (31-Jul-2023 11:09:47)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS THATISEELA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.68 | 1 | 4.68 | 3.55 | 0 (0%) | 0 | 0 | 3.55
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.78 | 0 | 0 | 0.25 | 0 (0%) | 0 | 0 | 0.25
3 | Drinking Water Supply | 1 | 0.93 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 1.83 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 1.03 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 1.93 | 1 | 1.93 | 2.52 | 0 (0%) | 0 | 0 | 2.52
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Compound Walls | 1 | 7.29 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Total | 9 | 19.24 | 2 | 6.61 | 6.31 | 0 (0%) | 0 | 0 | 6.31

## 16
R1.2 Component Wise Status Report as on (31-Jul-2023 11:10:02)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS DIGUVADERUVADA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 7.51 | 1 | 7.51 | 0.4 | 0 (0%) | 0 | 0 | 0.4
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.74 | 0 (0%) | 0 | 0 | 0.74
4 | Furniture for Students and Staff | 1 | 2.89 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.47 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 0.53 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 25.99 | 1 | 25.99 | 10.32 | 0 (0%) | 0 | 0 | 10.32
9 | Construction of Compound Walls | 1 | 15 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
11 | Kitchen Shed | 1 | 3.19 | 0 | 0 | 0.28 | 0 (0%) | 0 | 0 | 0.28
12 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01
13 | Total | 11 | 56.99 | 3 | 33.76 | 11.75 | 0 (0%) | 0 | 0 | 11.76

## 17
R1.2 Component Wise Status Report as on (31-Jul-2023 11:10:18)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS MALLUGUDA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.66 | 1 | 5.66 | 0.54 | 0 (0%) | 0 | 0 | 0.54
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.61 | 0 | 0 | 0.17 | 0 (0%) | 0 | 0 | 0.17
3 | Drinking Water Supply | 1 | 0.67 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 2.79 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.68 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 0.72 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 23.84 | 1 | 23.84 | 9.1 | 0 (0%) | 0 | 0 | 9.1
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 3.57 | 0 | 0 | 0.24 | 0 (0%) | 0 | 0 | 0.24
11 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.07
12 | Total | 10 | 39.45 | 2 | 29.5 | 10.05 | 0 (0%) | 0 | 0 | 10.12

## 18
R1.2 Component Wise Status Report as on (31-Jul-2023 11:10:30)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS GORATI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.52 | 1 | 4.52 | 0.59 | 0 (0%) | 0 | 0 | 0.59
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0.06 | 0 (0%) | 0 | 0 | 0.06
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.35 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.17 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 4.39 | 0 (0%) | 0 | 0 | 4.39
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 1.18 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
11 | Total | 10 | 24.97 | 2 | 17.52 | 5.04 | 0 (0%) | 0 | 0 | 5.04

## 19
R1.2 Component Wise Status Report as on (31-Jul-2023 11:10:52)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS(TW) VADAPUTTI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 7.88 | 1 | 7.88 | 1.39 | 0 (0%) | 0 | 0 | 1.39
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.49 | 0 | 0 | 0.06 | 0 (0%) | 0 | 0 | 0.06
3 | Drinking Water Supply | 1 | 0.85 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 2.78 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.5 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.07 | 1 | 2.07 | 0.58 | 0 (0%) | 0 | 0 | 0.58
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 2.48 | 0 (0%) | 0 | 0 | 2.48
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 0.64 | 1 | 0.64 | 0.07 | 0 (0%) | 0 | 0 | 0.07
11 | Total | 10 | 28.99 | 4 | 23.59 | 4.58 | 0 (0%) | 0 | 0 | 4.58

## 2
R1.2 Component Wise Status Report as on (31-Jul-2023 11:05:53)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS BEERUPADU
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.49 | 1 | 4.49 | 1.21 | 0 (0%) | 0 | 0 | 1.21
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0.27 | 0 (0%) | 0 | 0 | 0.27
3 | Drinking Water Supply | 1 | 0.31 | 1 | 0.31 | 0.58 | 0 (0%) | 0 | 0 | 0.58
4 | Furniture for Students and Staff | 1 | 1.47 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.9 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.03 | 1 | 2.03 | 1.47 | 0 (0%) | 0 | 0 | 1.47
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Kitchen Shed | 1 | 1.63 | 1 | 1.63 | 0.48 | 0 (0%) | 0 | 0 | 0.48
10 | Total | 9 | 11.98 | 4 | 8.46 | 4.02 | 0 (0%) | 0 | 0 | 4.02

## 20
R1.2 Component Wise Status Report as on (31-Jul-2023 11:11:04)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS THOLUKHARJA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.41 | 1 | 5.41 | 1.57 | 0 (0%) | 0 | 0 | 1.57
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.34 | 0 | 0 | 0.06 | 0 (0%) | 0 | 0 | 0.06
3 | Drinking Water Supply | 1 | 0.52 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 1.24 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 1.1 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 12.99 | 1 | 12.99 | 4.83 | 0 (0%) | 0 | 0 | 4.83
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 2.34 | 1 | 2.34 | 0.12 | 0 (0%) | 0 | 0 | 0.12
11 | Total | 10 | 24.99 | 3 | 20.75 | 6.58 | 0 (0%) | 0 | 0 | 6.58

## 21
R1.2 Component Wise Status Report as on (31-Jul-2023 11:11:24)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS BAYYADA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 6.25 | 1 | 6.25 | 0.76 | 0 (0%) | 0 | 0 | 0.76
2 | Drinking Water Supply | 1 | 0.79 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
3 | Furniture for Students and Staff | 1 | 1.8 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Major and Minor Repairs | 1 | 2.38 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 25.98 | 1 | 25.98 | 11.29 | 0 (0%) | 0 | 0 | 11.29
7 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Multiple Works Expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.16
9 | Total | 7 | 37.98 | 2 | 32.24 | 12.04 | 0 (0%) | 0 | 0 | 12.2

## 22
R1.2 Component Wise Status Report as on (31-Jul-2023 11:11:41)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : AIDED P S TADIKONDA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.58 | 1 | 5.58 | 2.23 | 0 (0%) | 0 | 0 | 2.23
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.41 | 0 | 0 | 0.06 | 0 (0%) | 0 | 0 | 0.06
3 | Drinking Water Supply | 1 | 0.44 | 1 | 0.44 | 0.55 | 0 (0%) | 0 | 0 | 0.55
4 | Furniture for Students and Staff | 1 | 2.57 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.42 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.32 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 5.16 | 0 (0%) | 0 | 0 | 5.16
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.07
10 | Total | 8 | 25 | 3 | 19.02 | 8 | 0 (0%) | 0 | 0 | 8.07

## 23
R1.2 Component Wise Status Report as on (31-Jul-2023 11:11:56)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS Y CHORUPALLI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.89 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.37 | 0 | 0 | 0.06 | 0 (0%) | 0 | 0 | 0.06
3 | Drinking Water Supply | 1 | 0.52 | 1 | 0.52 | 0.82 | 0 (0%) | 0 | 0 | 0.82
4 | Furniture for Students and Staff | 1 | 1.58 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.41 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 1.04 | 1 | 1.04 | 0.52 | 0 (0%) | 0 | 0 | 0.52
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 5.23 | 0 (0%) | 0 | 0 | 5.23
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 2.41 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
11 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.03
12 | Total | 10 | 24.99 | 3 | 14.56 | 6.63 | 0 (0%) | 0 | 0 | 6.66

## 24
R1.2 Component Wise Status Report as on (31-Jul-2023 11:12:13)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS VATHADA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.55 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.34 | 0 | 0 | 0.05 | 0 (0%) | 0 | 0 | 0.05
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 2.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.3 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.19 | 1 | 2.19 | 1.46 | 0 (0%) | 0 | 0 | 1.46
7 | Green Chalk Boards | 1 | 0.53 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 13 | 1 | 13 | 5.22 | 0 (0%) | 0 | 0 | 5.22
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 1.08 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
11 | Total | 10 | 25 | 2 | 15.19 | 6.73 | 0 (0%) | 0 | 0 | 6.73

## 25
R1.2 Component Wise Status Report as on (31-Jul-2023 11:12:36)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GTWAS BHADRAGIRI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 17.77 | 1 | 17.77 | 14.34 | 0 (0%) | 0 | 0 | 14.34
2 | Providing Electrification with Fans and Tube Lights | 1 | 4.69 | 1 | 4.69 | 3.18 | 0 (0%) | 0 | 0 | 3.18
3 | Drinking Water Supply | 1 | 1.27 | 1 | 1.27 | 0.99 | 0 (0%) | 0 | 0 | 0.99
4 | Furniture for Students and Staff | 1 | 17.76 | 1 | 17.76 | 9.39 | 0 (0%) | 0 | 0 | 9.39
5 | Painting to School | 1 | 7.63 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 17.32 | 1 | 17.32 | 7.46 | 0 (0%) | 0 | 0 | 7.46
7 | Green Chalk Boards | 1 | 1.06 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 60.99 | 1 | 60.99 | 12.3 | 0 (0%) | 0 | 0 | 12.3
9 | Construction of Compound Walls | 1 | 13.49 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.02
11 | Total | 9 | 141.99 | 6 | 119.8 | 47.67 | 0 (0%) | 0 | 0 | 47.7

## 26
R1.2 Component Wise Status Report as on (31-Jul-2023 11:12:54)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS IRIDI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.47 | 1 | 4.47 | 1.66 | 0 (0%) | 0 | 0 | 1.66
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.37 | 0 | 0 | 0.17 | 0 (0%) | 0 | 0 | 0.17
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 3.23 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.37 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 1.21 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 1 | 37 | 1 | 37 | 2.87 | 0 (0%) | 0 | 0 | 2.87
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 1.19 | 1 | 1.19 | 1.23 | 0 (0%) | 0 | 0 | 1.23
11 | Total | 10 | 49 | 3 | 42.66 | 5.93 | 0 (0%) | 0 | 0 | 5.93

## 27
R1.2 Component Wise Status Report as on (31-Jul-2023 10:33:45)
Executing Agency : --SELECT-- , Disrict Name : --SELECT-- , Mandal Name :All , School Name : All
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 14079 | 83521.01 | 13693 | 82250.36 | 51911.93 | 10 (0.07%) | 27.71 | 26.46 | 51938.4
2 | Providing Electrification with Fans and Tube Lights | 14023 | 19349.05 | 11427 | 16546.22 | 9175.45 | 62 (0.44%) | 66.61 | 48.37 | 9223.82
3 | Drinking Water Supply | 14208 | 33304.83 | 8292 | 21239.41 | 5349.02 | 1 (0.01%) | 2.62 | 3.78 | 5352.8
4 | Furniture for Students and Staff | 14131 | 51895.84 | 8318 | 34720.84 | 24388.61 | 59 (0.42%) | 193.44 | 141.71 | 24530.32
5 | Painting to School | 14083 | 28221.08 | 41 | 147.75 | 11.15 | 0 (0%) | 0 | 0 | 11.15
6 | Major and Minor Repairs | 14023 | 70857.96 | 12874 | 67868.45 | 38496.1 | 5 (0.04%) | 15.18 | 15.33 | 38511.43
7 | Green Chalk Boards | 14091 | 8100.41 | 674 | 361.67 | 185.75 | 0 (0%) | 0 | 0 | 185.75
8 | Construction of Additional Class Rooms (NABARD (RIDF XXV) through PC) | 8886 | 378900.13 | 8636 | 370769.62 | 120694.33 | 0 (0%) | 0 | 0 | 120694.33
9 | Construction of Compound Walls | 5998 | 52459.5 | 4525 | 40493.84 | 9876.07 | 2 (0.03%) | 2.61 | 1.15 | 9877.21
10 | English Labs | 8018 | 4089.18 | 129 | 65.79 | 26.42 | 0 (0%) | 0 | 0 | 26.42
11 | Kitchen Shed | 9231 | 20733.61 | 6369 | 16674.11 | 8362.45 | 51 (0.55%) | 51.71 | 36.44 | 8398.9
12 | Co-Located Anganwadi Centers | 4399 | 14822.26 | 4384 | 14781.72 | 1932.75 | 2 (0.05%) | 9.5 | 2.85 | 1935.6
13 | Multiple Works Expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1409.08
14 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1013.23
15 | Total | 135170 | 766254.86 | 79362 | 665919.8 | 270410.02 | 192 (0.14%) | 369.37 | 276.09 | 273108.43

## 3
R1.2 Component Wise Status Report as on (31-Jul-2023 11:06:16)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS MEDARAGANDA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.64 | 1 | 4.64 | 4.1 | 0 (0%) | 0 | 0 | 4.1
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.38 | 0 | 0 | 0.24 | 0 (0%) | 0 | 0 | 0.24
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.34 | 0 (0%) | 0 | 0 | 0.34
4 | Furniture for Students and Staff | 1 | 1.91 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.41 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.1 | 1 | 2.1 | 1.58 | 0 (0%) | 0 | 0 | 1.58
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Compound Walls | 1 | 10.12 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 1.51 | 1 | 1.51 | 1.01 | 0 (0%) | 0 | 0 | 1.01
11 | Total | 10 | 22.1 | 4 | 8.5 | 7.27 | 0 (0%) | 0 | 0 | 7.27

## 4
R1.2 Component Wise Status Report as on (31-Jul-2023 11:06:33)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS GORADA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.24 | 1 | 5.24 | 3.24 | 0 (0%) | 0 | 0 | 3.24
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.36 | 0 | 0 | 0.42 | 0 (0%) | 0 | 0 | 0.42
3 | Drinking Water Supply | 1 | 0.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 2.24 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 1.12 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2 | 1 | 2 | 1.87 | 0 (0%) | 0 | 0 | 1.87
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.02
10 | Total | 8 | 11.98 | 2 | 7.24 | 5.53 | 0 (0%) | 0 | 0 | 5.54

## 5
R1.2 Component Wise Status Report as on (31-Jul-2023 11:06:52)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS JARNA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.37 | 1 | 5.37 | 0.95 | 0 (0%) | 0 | 0 | 0.95
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.34 | 0 | 0 | 0.16 | 0 (0%) | 0 | 0 | 0.16
3 | Drinking Water Supply | 1 | 0.25 | 1 | 0.25 | 0.47 | 0 (0%) | 0 | 0 | 0.47
4 | Furniture for Students and Staff | 1 | 2.35 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.48 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 1.23 | 1 | 1.23 | 1.91 | 0 (0%) | 0 | 0 | 1.91
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Kitchen Shed | 1 | 1.21 | 1 | 1.21 | 0.22 | 0 (0%) | 0 | 0 | 0.22
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.02
11 | Total | 9 | 11.99 | 4 | 8.05 | 3.72 | 0 (0%) | 0 | 0 | 3.74

## 6
R1.2 Component Wise Status Report as on (31-Jul-2023 11:07:08)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS GEESADA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.28 | 1 | 4.28 | 2.68 | 0 (0%) | 0 | 0 | 2.68
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.53 | 1 | 0.53 | 0.3 | 0 (0%) | 0 | 0 | 0.3
3 | Drinking Water Supply | 1 | 0.19 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 1.61 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 1.06 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.4 | 1 | 2.4 | 1.75 | 0 (0%) | 0 | 0 | 1.75
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Kitchen Shed | 1 | 1.14 | 1 | 1.14 | 1.15 | 0 (0%) | 0 | 0 | 1.15
10 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.03
11 | Total | 9 | 11.99 | 4 | 8.35 | 5.88 | 0 (0%) | 0 | 0 | 5.9

## 7
R1.2 Component Wise Status Report as on (31-Jul-2023 11:07:27)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS REGIDI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 7.79 | 1 | 7.79 | 2.66 | 0 (0%) | 0 | 0 | 2.66
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.78 | 1 | 0.78 | 0.29 | 0 (0%) | 0 | 0 | 0.29
3 | Drinking Water Supply | 1 | 0.85 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 3.01 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 1.72 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 0.61 | 1 | 0.61 | 4.05 | 0 (0%) | 0 | 0 | 4.05
7 | Green Chalk Boards | 1 | 0.66 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Total | 8 | 15.93 | 3 | 9.18 | 7 | 0 (0%) | 0 | 0 | 7

## 8
R1.2 Component Wise Status Report as on (31-Jul-2023 11:07:50)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : MPPS ELWINPETA
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 5.04 | 1 | 5.04 | 2.9 | 0 (0%) | 0 | 0 | 2.9
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.59 | 0 | 0 | 0.26 | 0 (0%) | 0 | 0 | 0.26
3 | Drinking Water Supply | 1 | 0.9 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
4 | Furniture for Students and Staff | 1 | 1.32 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 1.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.11 | 1 | 2.11 | 1.45 | 0 (0%) | 0 | 0 | 1.45
7 | Green Chalk Boards | 1 | 0.26 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01
10 | Total | 8 | 11.99 | 2 | 7.14 | 4.61 | 0 (0%) | 0 | 0 | 4.61

## 9
R1.2 Component Wise Status Report as on (31-Jul-2023 11:08:05)
Executing Agency : --SELECT-- , Disrict Name : Manyam , Mandal Name :G.L.PURAM , School Name : GPS CH BINNIDI
Sl. No. | Work Type Name | Sanctioned Details |  | Inprogress Details |  |  | Completed |  |  | Total Expenditure
|  | No. of Works | Estimated Cost | No. of Works | Estimated Cost | Expenditure | No. of Works | Estimated Cost | Expenditure
1 | Construction of Toilet with Running Water | 1 | 4.97 | 1 | 4.97 | 3.67 | 0 (0%) | 0 | 0 | 3.67
2 | Providing Electrification with Fans and Tube Lights | 1 | 0.58 | 0 | 0 | 0.17 | 0 (0%) | 0 | 0 | 0.17
3 | Drinking Water Supply | 1 | 0.28 | 1 | 0.28 | 0.44 | 0 (0%) | 0 | 0 | 0.44
4 | Furniture for Students and Staff | 1 | 1.25 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
5 | Painting to School | 1 | 0.47 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
6 | Major and Minor Repairs | 1 | 2.57 | 1 | 2.57 | 2.11 | 0 (0%) | 0 | 0 | 2.11
7 | Green Chalk Boards | 1 | 0.4 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
8 | Construction of Compound Walls | 1 | 7.5 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
9 | English Labs | 1 | 0.51 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
10 | Kitchen Shed | 1 | 0.95 | 0 | 0 | 0 | 0 (0%) | 0 | 0 | 0
11 | Parents committee expenditure | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.06
12 | Total | 10 | 19.48 | 3 | 7.82 | 6.39 | 0 (0%) | 0 | 0 | 6.45

## Sheet32
Aided P S Lumbesu | 7.13 | 7.48
Aided P S Tadikonda | 6.89 | 6.97
Chemuduguda | 2.78 | 2.24
Chinaravikona | 2.69 | 1.96
Chinavankadara | 4.44 | 4.61
Duddukhallu | 3.56 | 2.25
Gadivonka Dara | 3.77 | 3.53
Goyapaka | 3.72 | 2.53
Gps Jk Padu Colny | 4.05 | 4.19
Gps Balesu | 3.18 | 2.95
Gps Beerupadu | 3.08 | 1.86
Gps Ch Binnidi | 4.72 | 4.73
Gps Geesada | 3.61 | 3.55
Gps Keesari | 4.6 | 4.03
Gps Lada | 3.68 | 3.72
Gps Medaraganda | 4.82 | 4.87
Gps Pedakharja | 4.03 | 4.21
Gps Tholukharja | 7.29 | 4.73
Gps Thota | 2.42 | 2.53
Gps Vangara | 4.56 | 3.46
Gps(Tw) Vadaputti | 5.22 | 2.47
Gtwas Bhadragiri | 31.85 | 32.99
Ijjakaai | 2.75 | 2.17
Iridi | 2.64 | 2.53
Kgbv G.L.Puram | 12.47 | 12.51
Kuntesu | 2.75 | 1.54
Lumbesu | 4.14 | 3.97
Mantrijyola | 3.71 | 2.01
Mpps Addamguda | 4.37 | 4.51
Mpps Bayyada | 10.55 | 8.87
Mpps Diguvaderuvada | 14.91 | 9.97
Mpps Elwinpeta | 3.53 | 3.51
Mpps Gorada | 3.14 | 2.76
Mpps Gorati | 7.42 | 3.94
Mpps Iridi | 1.8 | 3.53
Mpps Jarna | 2.57 | 2.29
Mpps Kanasingi | 3.28 | 3.3
Mpps Malluguda | 10.59 | 7.28
Mpps Regidi | 4.8 | 4.7
Mpps Savarakotapadu | 3.11 | 3.25
Mpps Thatiseela | 4.33 | 4.49
Mpps Vathada | 5.71 | 5.58
Mpps Y Chorupalli | 6.77 | 6.6
Tikkiabal | 4.05 | 3.87
Vadhaputti | 2.74 | 2.79
Vanakabhadi | 0.36 | 0.35
Vangara | 4.5 | 4.46

## Sheet33
7.13 | 7.48 | 0.33
3.28 | 3.3 | 5
3.68 | 3.72 | 1.78
2.42 | 2.53 | 2.09
3.11 | 3.25 | 2.74
4.05 | 4.19 | 2.62
4.33 | 4.49 | 1.98
14.91 | 9.97 | -3.16
10.59 | 7.28 | -0.54
7.42 | 3.94 | -2.38
5.22 | 2.47 | -0.64
3.08 | 1.86 | 0.94
7.29 | 4.73 | -0.71
10.55 | 8.87 | 1.49
6.89 | 6.97 | 1.11
6.77 | 6.6 | -0.14
5.71 | 5.58 | 1.02
31.85 | 32.99 | 15.82
1.8 | 3.53 | 4.13
4.82 | 4.87 | 2.45
3.14 | 2.76 | 2.39
2.57 | 2.29 | 1.15
3.61 | 3.55 | 2.27
4.8 | 4.7 | 2.2
3.53 | 3.51 | 1.08
4.72 | 4.73 | 1.67
167.27 | 150.16 | 46.69